## Module- Receipts
http://kopuramonline.com/Testing/ERP/chitfund/home.php
PROJECT NAME: | Kopuram Chits
MODULE NAME: | DUE-RECEIPTS
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Mohan
DATE OF CREATION: | 2019-02-15
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Receipt Duplication | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | 1.The receipt entries are duplicates at multiple time when the submit button clicked often by the user 2.submit button to hidden when the click is performed and it should be blocked with the receipt ID | pollachi KP10A november | CLOSED | HIGH | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D002 | add receipt entry-receipt amount field | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | user should not able to enter - these symbols it should be restricted |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D003 | In Payment type- | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type -Debit To field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D004 | branch name | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type -branch name field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D005 | cheque date | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type -cheque date field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D006 | In Payment type-DD | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type DD -cheque no field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D007 | branch name | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type -branch name field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D008 | cheque date | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type -cheque date field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D009 | In Payment type-RTGS/NEFT | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type RTGS/NEFT -debit to field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D010 | In Payment type-card | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | in payment type card -debit to field should be mandatory |  | CLOSED | MEDIUM | 15-02-2019 | Gowri | 18-02-2019 | VERIFIED
D011 | total pending amount | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | total pending amount doesn't changes it should be calculated according to the formula |  | CLOSED | HIGH | 18-02-2019 | Gowri | 18-02-2019 | VERIFIED
D012 | In Due receipt- Receipt generation | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | multiple clicks performed for multiple group the receipt is not generated |  | CLOSED | HIGH | 18-02-2019 | Gowri | 18-02-2019 | VERIFIED
D013 | In Due receipt- No Pending amount | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | If there is no pending amount the system accepts the operation and the receipt is generated. |  | CLOSED | HIGH | 17-02-2019 | Prasath | For client requirement its has been changed
D014 | In Due receipt- available advance amount | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | If the user can entry the amount even there is no pending the system didn't calculate with the available advance amount |  | CLOSED | HIGH | 17-02-2019 | Prasath | As per Client requirements
D015 | In Due Receipt-Splitup table Total | http://kopuramonline.com/Testing/ERP/chitfund/cheque_tracking.php | total amount didn't calculated |  | CLOSED | HIGH | 17.02.2019 | Prasath | 18-02-2019 | VERIFIED

## Module-Advance Receipts
http://kopuramonline.com/Testing/ERP/chitfund/home.php
PROJECT NAME: | Kopuram Chits
MODULE NAME: | Advance receipts
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Mohan
DATE OF CREATION: | 2019-02-16
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Receipt Duplication | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | 1.The receipt entries are duplicates at multiple time when the submit button clicked often by the user 2.submit button to be hidden when the click is performed by the user and it should be blocked with the receipt ID | pollachi KP10A november | CLOSED | HIGH | 15-02-2019 | Prasath | 18-02-2019
D002 | submit button | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | when submit button clicks the system shows 404 error message |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D003 | add advance receipt entry-receipt amount field | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | user should not able to enter " - these symbols it should be restricted |  | CLOSED | HIGH | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D004 | In Payment type- | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type -Debit To field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D005 | branch name | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type -branch name field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D006 | cheque date | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type -cheque date field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D007 | In Payment type-DD | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type DD -cheque no field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D008 | branch name | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type -branch name field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D009 | cheque date | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type -cheque date field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D010 | In Payment type-RTGS/NEFT | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type RTGS/NEFT -debit to field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D011 | In Payment type-card | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | in payment type card -debit to field should be mandatory |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 18-02-2019 | VERIFIED
D012 | View advance receipt-all branch | http://kopuramonline.com/Testing/ERP/chitfund/advanced_receipt_new.php | all branch not showing |  | CLOSED | MEDIUM | 16-02-2019 | Prasath | 19-02-2019 | VERIFIED

## Module-Add advance Adjustment R
http://kopuramonline.com/Testing/ERP/chitfund/home.php
PROJECT NAME: | KopuramChits
MODULE NAME: | Add advance Adjustment Receipts
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Mohan
DATE OF CREATION: | 2019-02-16
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | total pending amount | http://kopuramonline.com/Testing/ERP/chitfund/advance_adjustment.php | total pending amount doesn't changes it should be calculated according to the formula | udumalpet kalishwari | CLOSED | HIGH | 18-02-2019 | Gowri | 18-02-2019 | VERIFIED
D002 | add advance receipt entry-receipt amount field | http://kopuramonline.com/Testing/ERP/chitfund/advance_adjustment.php | user should not able to enter " - these symbols it should be restricted |  | CLOSED | HIGH | 18-02-2019 | Gowri | 18-02-2019 | VERIFIED

## Master- Add Group
http://kopuramonline.com/Testing/chitfund/groupcreation.php
PROJECT NAME: | KopuramChits
MODULE NAME: | Add Group
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Gowri
DATE OF CREATION: | 19-02-2019
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Add Group- Group Category Field | http://kopuramonline.com/Testing/chitfund/groupcreation.php | in Group Category field should be mandatory |  | CLOSED | MEDIUM | 19-02-2019 | Gowri | 19-02-2019
D002 | Add Group- Select Branch | http://kopuramonline.com/Testing/chitfund/groupcreation.php | in Select Branch field should be mandatory |  | CLOSED | MEDIUM | 19-02-2019 | Gowri | 19-02-2019
D003 | Delete Group- Remarks field | http://kopuramonline.com/Testing/chitfund/remark_group.php?do=delete&id=170 | in Remarks field should be mandatory |  | CLOSED | MEDIUM | 19-02-2019 | Gowri | 19-02-2019
D004 | Edit Group- Ending Date Field | http://kopuramonline.com/Testing/chitfund/editgroup.php?id=170 | In Ending date field depend upon starting date. Ending date values wrongly calculated from starting date values. |  | CLOSED | HIGH | 19-02-2019 | Prasanth | 19-02-2019
D005 | View Non-Started Group details | http://kopuramonline.com/Testing/chitfund/viewgroupcreation.php?step=restart | View Group page in start button multiple time clicked duplicate entries are occured |  | CLOSED | HIGH | 20-02-2019 | Prasanth | 20-02-2019

## Module Enrollment
http://kopuramonline.com/Testing/chitfund/addauctionchit_enrl.php
PROJECT NAME: | KopuramChits
MODULE NAME: | Module- Enrollment
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Mohan & Gowri
DATE OF CREATION: | 2019-02-19
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Add Entrollment Duplication | http://kopuramonline.com/Testing/chitfund/addauctionchit_enrl.php | 1.The group entrollment entries are duplicates at multiple time when the submit button clicked often by the user | GV-KOP-2019 | CLOSED | HIGH | 20-02-2019 | Prasath | 20-02-2019 | VERIFIED | Gowri Tested
D002 | Add Entrollment - Pending ticket issues | http://kopuramonline.com/Testing/chitfund/addauctionchit_enrl.php | If pending tickets is 0.5 or 1 then the ticket type should display as per the ticket quantity | GV-TEST-2019 | CLOSED | HIGH | 20-02-2019 | Prasath | 20-02-2019 | VERIFIED | Gowri Tested
D003 | Add Entrollment Page- Group name issues | http://kopuramonline.com/Testing/chitfund/addauctionchit_enrl.php | Group name depends upon Branch Name but this page not properly connected with branch type | GV-POL-2019- Pollachi Branch. But Udumalpet Branch also showing GV-POL-2019 Name and GV-UDM-2019 udumalpet group not showing | CLOSED | HIGH | 22-02-2019 | Prasath | 22-02-2019 | VERIFIED | Gowri Tested
D004 | View Entrollment Page | http://kopuramonline.com/Testing/chitfund/viewauctionenrolls.php?step=delete | When Delete button clicked alert message showing on red color so change to green color |  | CLOSED | MEDIUM | 22-02-2019 | Gowri | 22-02-2019 | VERIFIED | Gowri Tested
D005 | Add Entrollment Page- Backend issues | http://kopuramonline.com/Testing/chitfund/addauctionchit_enrl.php | When Nominees details filled in entrollment page that time datas not stored in database. |  | CLOSED | HIGH | 22-02-2019 | Prasath | 22-02-2019 | VERIFIED | Gowri Tested
D006 | view Entrollment Page- edit | http://kopuramonline.com/Testing/chitfund/viewauctionenrolls.php | edit option is not working |  | CLOSED | MEDIUM | 22.02.2019 | Prasath | 25-2-19 |  | Gowri Tested

## Reports- Vacant Report
http://kopuramonline.com/Testing/chitfund/report_vacant_fill.php
PROJECT NAME: | KopuramChits
MODULE NAME: | REPORTS-Vacant Report
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Gowri
DATE OF CREATION: | 2019-02-20
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Fill Group In vacant Report | http://kopuramonline.com/Testing/chitfund/report_vacant_fill.php | When Fill group button is clicked multiple time duplication occurs | GV-KOP-2019 | CLOSED | HIGH | 20-02-2019 | Prasath | 22-02-2019 | VERIFIED

## Module- Auction Details
http://kopuramonline.com/Testing/chitfund/view_double_chit.php
PROJECT NAME: | KopuramChits
MODULE NAME: | Module- Auction Details
REFERENCE DOCUMENT: | NO DOCS
CREATED BY: | Gowri
DATE OF CREATION: | 2019-02-21
DEFECT ID | TEST TITLE | URL | BUGS | TEST DATA | STATUS | PRIORITY | DEFECT DATE | ASSIGNED TO | FIXED DATE | VERIFIED / RE-VERIFIED
D001 | Add Auction Entry | http://kopuramonline.com/Testing/chitfund/add_double_chit.php | 1.Commission Amount depends on Chit values * Commission percentage. 2. Bidding Amount greater than commission amount. if it is less than show on red color or alert msg. |  | CLOSED | HIGH | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D002 | Request for Approval - for First Payment Release | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=954 | In Customer Branch Id should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D003 | Request for Approval - for First Payment Release | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=954 | In Employee Branch Id should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D004 | Request for Approval - for First Payment Release | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=954 | In Customer Name should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D005 | Request for Approval - for First Payment Release | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=954 | In Date format Error in database | Actual values: 21-02-2019, But Experted: 02/21/2019 | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D006 | Part Payment Page | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Company Pending Amount not properly calculated. | In GV-KOP-2019: Correct Values: 9800 but Showing values: 0 | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D007 | Part Payment Page | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Customer Branch Id should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D008 | Part Payment Page | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Employee Branch Id should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D009 | Part Payment Page | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Customer Name should be Stored on Database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D010 | Part Payment Page | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Date format Error in database |  | CLOSED | MEDIUM | 21-02-2019 | Prasanth | 26-2-2019 |  | Gowri Tested
D011 | After Approve part payment | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In Total Released Amount not correctly calculated |  | CLOSED | HIGH | 21-02-2019 | Prasanth | 22-2-2019 | VERIFIED | Gowri Tested
D012 | closed group issue | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | If group is closed the receipt cannot be generated |  | CLOSED | HIGH | 22-02-2019 | Prasanth | 23-02-2019 | VERIFIED
D013 | Groupwise outstanding report | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | In outstanding report If group is closed its not displayed |  | CLOSED | HIGH | 22-02-2019 | Prasanth | 23-02-19 | VERIFIED
D014 | bid amont field | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=950 | only integers should should accept |  | CLOSED | MEDIUM | 22-02-2019 | Prasanth | 23-02-2019 | VERIFIED
D015 | Auction Type- Duplicate | http://kopuramonline.com/Testing/chitfund/add_double_chit.php | If Slab register group means in auction entry page duplicate not showing datas |  | CLOSED | HIGH | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED | Gowri Tested
D016 | auction -send for approval-chit payemnt entry | http://kopuramonline.com/Testing/chitfund/add_double_chit.php | pending amount-charcters & symbols are allowed it should validated |  | CLOSED | HIGH | 25-02-2019 | Prasanth | 25-02-2019 | VERIFIED
D017 | Notification- Request For Approval Page | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=987 | If Multiple time Clicked Submit button in Request for approval page Sending duplicate notification occures |  | CLOSED | HIGH | 25-02-2019 | Gowri & Prasanth | 26-02-2019 | VERIFIED | Gowri Tested
D018 | Notification- Request For Approval Page | http://kopuramonline.com/Testing/chitfund/boot_modal.php?id=987 | In part payment-chit payment approval is rejected and the total company release amount is still existing |  | CLOSED | HIGH | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED
D019 | part payment-company release amount | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=963 | in company release amount-only integers should should accept- |  | CLOSED | MEDIUM | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED
D020 | part payment-payment type | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=963 | payment type should be set as mandatory |  | CLOSED | HIGH | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED
D021 | part payment-payment type | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=963 | payment type -cheque,dd,NEFT,CARD in these types the debit to field should be set as mandatory field |  | CLOSED | MEDIUM | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED
D022 | Adjust with another group | http://kopuramonline.com/Testing/chitfund/part_boot_modal_approval.php?id=963 | enter due amount field should accept only integers |  | CLOSED | MEDIUM | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED
D023 | edit | http://kopuramonline.com/Testing/chitfund/edit_double_chit.php?id=965 | bid amount field should accept only integers |  | CLOSED | MEDIUM | 25-02-2019 | Prasanth | 26-02-2019 | VERIFIED